- My priorities over the next few weeks:
  - Get Steve up to speed on SFL, confocal, and image analysis
  - Determine if I have to finish any experiments for my thesis as currently outlined, or if anything needs to be added or cut.
  - Write thesis and produce figures.

---
September: First Pass Through Thesis
8/29 - 9/4
9/5 - 9/11
9/12 - 9/18
9/19 - 9/25
9/26 - 10/2
Janus Fab
Practice
Particle collect /
processing
Clean room
training
Clean room
training
Confocal training
Finish analysis
of rod data
New rod experiments
if necessary
Analyze any new data;
New images if
needed
Outline content;
Decide cuts?
Intro +
Lit Review
Chapter 5:
Complex
particles
Chapter 2:
Tracking
Algorithms
Chapter 3:
Rod-shaped
Colloids
Confocal piezo arrives?
Fix confocal!
Job Interviews
(R and Riverbed)
Wolfram
interview?
Coordinate w/ Scott
On DNA paper
Training Steve
Lab for Thesis
Writing
Misc
Key:

---
October: Finish Thesis and Editing
10/3 - 10/9
10/10 - 10/16
10/17 - 10/23
10/24 - 10/30
Software primer
(Matlab, Clewin,
etc)
Basic analysis of
confocal data
Support on
experiments
If at all possible, no experiments this month
Appendices
Editing; may
Include new data
Editing; may
Include new data
Editing!
Give to JAL.
Close down my
lab space.
Training Steve
Lab for Thesis
Writing
Misc
Key:

---
Thesis decisions
- Experiments
  - Need to finish analyzing rod tracking data I have!
  - Decide if new data is needed: start doing this ASAP if so.
  - Determine if we need higher-quality particle images: obtain if so.
- Computational
  - Algorithm is developed for tracking other shapes, but the programming isn't. Very difficult to get right.
  - How necessary is this? Do we drop it or deprioritize?
  - Note: I want this section, but not as much as I want to graduate.
- Is anything else necessary?

---
- What should Steve be working on?
  - My experiments are almost done for the thesis as defined. At most, I will need:
    - A few more rod diffusion experiments (take a couple days)
    - A few good images of Janus rods or other particles, if current ones don't serve
  - These are not useful for him, except as SFL practice.
- My suggestion: start him on “mini-project” with defined goal.
  - One idea: hydrophobic-patterned substrate, let rods assemble on this.
  - Another: Set up “PnP” SFL, get him talking to Rogers group early.